## transformation_plans
business_id | phase | action | solution_id | start_month | duration_months | expected_cost | expected_savings | expected_emission_reduction | expected_water_saving | owner_role | dependency | status
B001 | Phase 1 - Quick Wins | Source Waste Segregation & Colour-Coded Bins | sol-waste-segregation | 1 | 2 | 129000 | 192000 | 13.66 | 0 | EHS Officer | Baseline data from Climate Assessment | Completed
B001 | Phase 1 - Quick Wins | AI Delivery Route Dispatch & Load Optimization | sol-route-opt | 3 | 3 | 75000 | 94000 | 5.39 | 0 | Logistics Manager | Baseline data from Climate Assessment | Completed
B001 | Phase 1 - Quick Wins | Smart Ultrasonic Water Leak & Flow Telemetry | sol-leak-sensors | 6 | 3 | 298000 | 172000 | 4.28 | 438599 | EHS Officer | Baseline data from Climate Assessment | Completed
B001 | Phase 1 - Quick Wins | High-Bay Smart Daylight-Linked LED Lighting | sol-led-iot | 9 | 3 | 360000 | 180000 | 17.2 | 0 | Plant Head | Baseline data from Climate Assessment | Completed
B001 | Phase 2 - Efficiency Improvements | IoT Smart Sub-Metering & Energy Dashboard | sol-smart-metering | 4 | 3 | 340000 | 210000 | 9.8 | 0 | Plant Head | Baseline data from Climate Assessment | In Progress
B001 | Phase 2 - Efficiency Improvements | HVAC & Cold-Chain Optimization | sol-hvac-optimization | 7 | 5 | 654000 | 267000 | 26.39 | 0 | Energy Manager | Baseline data from Climate Assessment | In Progress
B001 | Phase 2 - Efficiency Improvements | VFD & IE4 Super-Premium Motors Retrofit | sol-machinery-vfd | 12 | 3 | 1131000 | 412000 | 37.92 | 0 | Energy Manager | Sub-metering baseline from sol-smart-metering preferred | In Progress
B001 | Phase 2 - Efficiency Improvements | Rooftop Rainwater Harvesting & Recharge Well | sol-rainwater | 15 | 6 | 548000 | 198000 | 5.85 | 1023397 | EHS Officer | Baseline data from Climate Assessment | In Progress
B001 | Phase 2 - Efficiency Improvements | Effluent Treatment Plant Optimization | sol-etp-optimization | 21 | 6 | 1044000 | 324000 | 10.28 | 438599 | EHS Officer | Wastewater flow survey | In Progress
B001 | Phase 2 - Efficiency Improvements | Closed-Loop Water Recycling & Ultrafiltration | sol-water-ro | 27 | 10 | 2663000 | 668000 | 19.01 | 3905617 | EHS Officer | ETP stabilisation before return line commissioning | In Progress
B001 | Phase 3 - Circularity | Textile Fabric Off-Cut Circular Recovery & Baling | sol-waste-recovery | 8 | 3 | 466000 | 331000 | 25.15 | 0 | EHS Officer | Segregation at source must be running | Planned
B001 | Phase 3 - Circularity | Sustainable / Light-Weight Packaging Design | sol-sustainable-packaging | 11 | 4 | 599000 | 250000 | 26.45 | 0 | Procurement Lead | Customer drop-test / specification approval | Planned
B001 | Phase 4 - Renewable / Mobility Transition | Rooftop Solar PV System (75 kWp) | sol-solar | 12 | 6 | 3118000 | 920000 | 89.01 | 0 | Energy Manager | Roof structural survey + DISCOM net-metering application | Planned
B001 | Phase 4 - Renewable / Mobility Transition | Commercial EV Cargo Van Transition (Phase 1) | sol-ev-fleet | 18 | 6 | 1364000 | 312000 | 16.11 | 0 | Logistics Manager | Charging infrastructure and depot power sanction | Planned
B001 | Phase 5 - Verification | Metering calibration, data reconciliation & third-party review of reported outcomes | N/A | 15 | 3 | 180000 | 0 | 0 | 0 | Sustainability Coordinator | At least 6 months of post-implementation meter readings | In Progress
B002 | Phase 1 - Quick Wins | Source Waste Segregation & Colour-Coded Bins | sol-waste-segregation | 1 | 2 | 83000 | 122000 | 8.72 | 0 | EHS Officer | Baseline data from Climate Assessment | In Progress
B002 | Phase 1 - Quick Wins | AI Delivery Route Dispatch & Load Optimization | sol-route-opt | 3 | 3 | 138000 | 174000 | 9.96 | 0 | Logistics Manager | Baseline data from Climate Assessment | In Progress
B002 | Phase 1 - Quick Wins | Smart Ultrasonic Water Leak & Flow Telemetry | sol-leak-sensors | 6 | 3 | 100000 | 58000 | 1.43 | 147000 | EHS Officer | Baseline data from Climate Assessment | In Progress
B002 | Phase 1 - Quick Wins | High-Bay Smart Daylight-Linked LED Lighting | sol-led-iot | 9 | 3 | 159000 | 79000 | 7.58 | 0 | Plant Head | Baseline data from Climate Assessment | In Progress
B002 | Phase 2 - Efficiency Improvements | IoT Smart Sub-Metering & Energy Dashboard | sol-smart-metering | 4 | 3 | 150000 | 92000 | 4.32 | 0 | Plant Head | Baseline data from Climate Assessment | Planned
B002 | Phase 2 - Efficiency Improvements | Compressed Air System Optimization | sol-compressed-air | 7 | 3 | 162000 | 92000 | 9.21 | 0 | Energy Manager | Baseline data from Climate Assessment | Planned
B002 | Phase 2 - Efficiency Improvements | VFD & IE4 Super-Premium Motors Retrofit | sol-machinery-vfd | 10 | 3 | 424000 | 155000 | 14.21 | 0 | Energy Manager | Sub-metering baseline from sol-smart-metering preferred | Planned
B002 | Phase 2 - Efficiency Improvements | Rooftop Rainwater Harvesting & Recharge Well | sol-rainwater | 13 | 6 | 184000 | 66000 | 1.96 | 343000 | EHS Officer | Baseline data from Climate Assessment | Planned
B002 | Phase 2 - Efficiency Improvements | Effluent Treatment Plant Optimization | sol-etp-optimization | 19 | 6 | 350000 | 108000 | 3.44 | 147000 | EHS Officer | Wastewater flow survey | Planned
B002 | Phase 3 - Circularity | Textile Fabric Off-Cut Circular Recovery & Baling | sol-waste-recovery | 8 | 3 | 297000 | 211000 | 16.04 | 0 | EHS Officer | Segregation at source must be running | Planned
B002 | Phase 4 - Renewable / Mobility Transition | Rooftop Solar PV System (75 kWp) | sol-solar | 12 | 6 | 1168000 | 345000 | 33.36 | 0 | Energy Manager | Roof structural survey + DISCOM net-metering application | Planned
B002 | Phase 4 - Renewable / Mobility Transition | Commercial EV Cargo Van Transition (Phase 1) | sol-ev-fleet | 18 | 6 | 2521000 | 576000 | 29.77 | 0 | Logistics Manager | Charging infrastructure and depot power sanction | Planned
B002 | Phase 5 - Verification | Metering calibration, data reconciliation & third-party review of reported outcomes | N/A | 15 | 3 | 180000 | 0 | 0 | 0 | Sustainability Coordinator | At least 6 months of post-implementation meter readings | Planned
B003 | Phase 1 - Quick Wins | Source Waste Segregation & Colour-Coded Bins | sol-waste-segregation | 1 | 2 | 75000 | 110000 | 7.88 | 0 | EHS Officer | Baseline data from Climate Assessment | Completed
B003 | Phase 1 - Quick Wins | AI Delivery Route Dispatch & Load Optimization | sol-route-opt | 3 | 3 | 69000 | 87000 | 4.95 | 0 | Logistics Manager | Baseline data from Climate Assessment | Completed
B003 | Phase 1 - Quick Wins | Smart Ultrasonic Water Leak & Flow Telemetry | sol-leak-sensors | 6 | 3 | 100000 | 58000 | 1.43 | 147000 | EHS Officer | Baseline data from Climate Assessment | Completed
B003 | Phase 1 - Quick Wins | High-Bay Smart Daylight-Linked LED Lighting | sol-led-iot | 9 | 3 | 223000 | 111000 | 10.65 | 0 | Plant Head | Baseline data from Climate Assessment | Completed
B003 | Phase 2 - Efficiency Improvements | IoT Smart Sub-Metering & Energy Dashboard | sol-smart-metering | 4 | 3 | 210000 | 130000 | 6.07 | 0 | Plant Head | Baseline data from Climate Assessment | In Progress
B003 | Phase 2 - Efficiency Improvements | HVAC & Cold-Chain Optimization | sol-hvac-optimization | 7 | 5 | 325000 | 133000 | 13.14 | 0 | Energy Manager | Baseline data from Climate Assessment | In Progress
B003 | Phase 2 - Efficiency Improvements | VFD & IE4 Super-Premium Motors Retrofit | sol-machinery-vfd | 12 | 3 | 563000 | 205000 | 18.88 | 0 | Energy Manager | Sub-metering baseline from sol-smart-metering preferred | In Progress
B003 | Phase 2 - Efficiency Improvements | Rooftop Rainwater Harvesting & Recharge Well | sol-rainwater | 15 | 6 | 184000 | 66000 | 1.96 | 343000 | EHS Officer | Baseline data from Climate Assessment | In Progress
B003 | Phase 2 - Efficiency Improvements | Closed-Loop Water Recycling & Ultrafiltration | sol-water-ro | 21 | 10 | 892000 | 224000 | 6.37 | 1309000 | EHS Officer | ETP stabilisation before return line commissioning | In Progress
B003 | Phase 3 - Circularity | Sustainable / Light-Weight Packaging Design | sol-sustainable-packaging | 8 | 4 | 771000 | 322000 | 34.05 | 0 | Procurement Lead | Customer drop-test / specification approval | Planned
B003 | Phase 3 - Circularity | Organic Waste Composting / Small Biogas Unit | sol-composting-biogas | 12 | 5 | 478000 | 164000 | 26.99 | 0 | EHS Officer | Segregation at source must be running | Planned
B003 | Phase 4 - Renewable / Mobility Transition | Rooftop Solar PV System (75 kWp) | sol-solar | 12 | 6 | 1552000 | 458000 | 44.32 | 0 | Energy Manager | Roof structural survey + DISCOM net-metering application | Planned
B003 | Phase 4 - Renewable / Mobility Transition | Commercial EV Cargo Van Transition (Phase 1) | sol-ev-fleet | 18 | 6 | 1253000 | 286000 | 14.8 | 0 | Logistics Manager | Charging infrastructure and depot power sanction | Planned
B003 | Phase 5 - Verification | Metering calibration, data reconciliation & third-party review of reported outcomes | N/A | 15 | 3 | 180000 | 0 | 0 | 0 | Sustainability Coordinator | At least 6 months of post-implementation meter readings | In Progress
B004 | Phase 1 - Quick Wins | AI Delivery Route Dispatch & Load Optimization | sol-route-opt | 1 | 3 | 40000 | 51000 | 2.91 | 0 | Logistics Manager | Baseline data from Climate Assessment | Completed
B004 | Phase 1 - Quick Wins | Smart Ultrasonic Water Leak & Flow Telemetry | sol-leak-sensors | 4 | 3 | 100000 | 58000 | 1.43 | 147000 | EHS Officer | Baseline data from Climate Assessment | Completed
B004 | Phase 1 - Quick Wins | High-Bay Smart Daylight-Linked LED Lighting | sol-led-iot | 7 | 3 | 189000 | 94000 | 9.01 | 0 | Plant Head | Baseline data from Climate Assessment | Completed
B004 | Phase 2 - Efficiency Improvements | IoT Smart Sub-Metering & Energy Dashboard | sol-smart-metering | 4 | 3 | 178000 | 110000 | 5.13 | 0 | Plant Head | Baseline data from Climate Assessment | In Progress
B004 | Phase 2 - Efficiency Improvements | Compressed Air System Optimization | sol-compressed-air | 7 | 3 | 150000 | 86000 | 8.55 | 0 | Energy Manager | Baseline data from Climate Assessment | In Progress
B004 | Phase 2 - Efficiency Improvements | VFD & IE4 Super-Premium Motors Retrofit | sol-machinery-vfd | 10 | 3 | 394000 | 144000 | 13.2 | 0 | Energy Manager | Sub-metering baseline from sol-smart-metering preferred | In Progress
B004 | Phase 2 - Efficiency Improvements | Rooftop Rainwater Harvesting & Recharge Well | sol-rainwater | 13 | 6 | 184000 | 66000 | 1.96 | 343000 | EHS Officer | Baseline data from Climate Assessment | In Progress
B004 | Phase 3 - Circularity | Sustainable / Light-Weight Packaging Design | sol-sustainable-packaging | 8 | 4 | 577000 | 241000 | 25.49 | 0 | Procurement Lead | Customer drop-test / specification approval | Planned
B004 | Phase 4 - Renewable / Mobility Transition | Rooftop Solar PV System (75 kWp) | sol-solar | 12 | 6 | 1085000 | 320000 | 30.97 | 0 | Energy Manager | Roof structural survey + DISCOM net-metering application | Planned
B004 | Phase 5 - Verification | Metering calibration, data reconciliation & third-party review of reported outcomes | N/A | 15 | 3 | 180000 | 0 | 0 | 0 | Sustainability Coordinator | At least 6 months of post-implementation meter readings | In Progress
B005 | Phase 1 - Quick Wins | Source Waste Segregation & Colour-Coded Bins | sol-waste-segregation | 1 | 2 | 44000 | 65000 | 4.62 | 0 | EHS Officer | Baseline data from Climate Assessment | In Progress
B005 | Phase 1 - Quick Wins | AI Delivery Route Dispatch & Load Optimization | sol-route-opt | 3 | 3 | 40000 | 51000 | 2.91 | 0 | Logistics Manager | Baseline data from Climate Assessment | In Progress
B005 | Phase 1 - Quick Wins | Smart Ultrasonic Water Leak & Flow Telemetry | sol-leak-sensors | 6 | 3 | 100000 | 58000 | 1.43 | 147000 | EHS Officer | Baseline data from Climate Assessment | In Progress
B005 | Phase 1 - Quick Wins | High-Bay Smart Daylight-Linked LED Lighting | sol-led-iot | 9 | 3 | 137000 | 69000 | 6.55 | 0 | Plant Head | Baseline data from Climate Assessment | In Progress
B005 | Phase 2 - Efficiency Improvements | IoT Smart Sub-Metering & Energy Dashboard | sol-smart-metering | 4 | 3 | 130000 | 80000 | 3.73 | 0 | Plant Head | Baseline data from Climate Assessment | Planned
B005 | Phase 2 - Efficiency Improvements | HVAC & Cold-Chain Optimization | sol-hvac-optimization | 7 | 5 | 228000 | 93000 | 9.18 | 0 | Energy Manager | Baseline data from Climate Assessment | Planned
B005 | Phase 2 - Efficiency Improvements | VFD & IE4 Super-Premium Motors Retrofit | sol-machinery-vfd | 12 | 3 | 394000 | 144000 | 13.2 | 0 | Energy Manager | Sub-metering baseline from sol-smart-metering preferred | Planned
B005 | Phase 2 - Efficiency Improvements | Rooftop Rainwater Harvesting & Recharge Well | sol-rainwater | 15 | 6 | 184000 | 66000 | 1.96 | 343000 | EHS Officer | Baseline data from Climate Assessment | Planned
B005 | Phase 2 - Efficiency Improvements | Effluent Treatment Plant Optimization | sol-etp-optimization | 21 | 6 | 350000 | 108000 | 3.44 | 147000 | EHS Officer | Wastewater flow survey | Planned
B005 | Phase 3 - Circularity | Textile Fabric Off-Cut Circular Recovery & Baling | sol-waste-recovery | 8 | 3 | 158000 | 112000 | 8.5 | 0 | EHS Officer | Segregation at source must be running | Planned
B005 | Phase 3 - Circularity | Sustainable / Light-Weight Packaging Design | sol-sustainable-packaging | 11 | 4 | 474000 | 198000 | 20.95 | 0 | Procurement Lead | Customer drop-test / specification approval | Planned
B005 | Phase 4 - Renewable / Mobility Transition | Rooftop Solar PV System (75 kWp) | sol-solar | 12 | 6 | 1085000 | 320000 | 30.97 | 0 | Energy Manager | Roof structural survey + DISCOM net-metering application | Planned
B005 | Phase 5 - Verification | Metering calibration, data reconciliation & third-party review of reported outcomes | N/A | 15 | 3 | 180000 | 0 | 0 | 0 | Sustainability Coordinator | At least 6 months of post-implementation meter readings | Planned